## Gantt Chart Template
| GANTT CHART | [21 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | PROJECT CONCORD
| DATE | 12/03/2022
|  | PHASE ONE | [14 empty] | PHASE TWO | [13 empty] | PHASE THREE | [15 empty] | PHASE FOUR | [25 empty] | PHASE FIVE | [20 empty] | PHASE SIX
| TEAM MEMBER | WEEK 1 | [7 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [8 empty] | WEEK 7 |  |  |  |  | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14
|  | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su
|  | 4/3 | [13 empty] | 18/3 | 19/3 | [12 empty] | 1/4 | 2/4 | [14 empty] | 17/4 | 18/4 | [24 empty] | 13/5 | 14/5 | [19 empty] | 3/6 | 4/6 | [7 empty] | 12/6
GEORGIOS AGGELOPOULOS
[6 empty] | 0.1.1 | [15 empty] | 0.2.2 | [6 empty] | 0.2.5 | [6 empty] | 0.3.2 | [8 empty] | 0.3.5 |  |  |  |  | 0.4.1 | [7 empty] | 0.4.3 | [10 empty] | 0.4.5 | [5 empty] | 0.5.1 | [12 empty] | 0.5.2 | [7 empty] | 1.0.1
[15 empty] | 0.1.5 | [9 empty] | 0.2.3 | [37 empty] | 0.4.6
| VASILIOS DELALIS | WEEK 3 Su: 0.2.1; WEEK 5 M: 0.3.1
|  |  |  | 0.1.1 | [17 empty] | 0.2.2 | [5 empty] | 0.2.4 | [7 empty] | 0.3.3 | [8 empty] | 0.3.5 | [8 empty] | 0.4.3 | [12 empty] | 0.4.6 | [22 empty] | 0.5.3 | [9 empty] | 1.0.3
[15 empty] | 0.1.4 | [53 empty] | 0.4.5
| NIKOLAOS KANTAS | WEEK 3 Su: 0.2.1; WEEK 5 M: 0.3.1
[13 empty] | 0.1.2 | [8 empty] | 0.2.2 | [5 empty] | 0.2.4 | [12 empty] | 0.3.4 | [11 empty] | 0.4.2 | [12 empty] | 0.4.4 | [5 empty] | 0.4.6 | [15 empty] | 0.5.3 | [10 empty] | 1.0.2
MARIA KONSTANTINA BIZOUMI
[13 empty] | 0.1.4 | [8 empty] | 0.2.2 | [6 empty] | 0.2.5 | [6 empty] | 0.3.3 | [19 empty] | 0.4.2 | [11 empty] | 0.4.5 | [18 empty] | 0.5.2 | [8 empty] | 1.0.1
0.3.4
| ALEXANDROS PANAGIOTIS SOILEMEZIDIS | WEEK 3 Su: 0.2.1; WEEK 5 M: 0.3.1
[9 empty] | 0.1.1 | [12 empty] | 0.2.2 | [13 empty] | 0.3.2 | [8 empty] | 0.3.5 |  |  |  |  | 0.4.1 | [21 empty] | 0.4.6 |  |  |  |  | 0.5.1 | [13 empty] | 0.5.3 | [7 empty] | 1.0.2
[11 empty] | 0.1.5 | [13 empty] | 0.2.3 | [30 empty] | 0.4.3
WBS LEGEND
WBS NUMBER | TASK TITLE
0.1 | Phase 1
0.1.1 | Compose Detailed Description
0.1.2 | Create PERT / Gantt Charts
0.1.4 | Compose Risk Assessment/ Team RA
0.1.5 | Compose Feasibility Study
0.2 | Phase 2
0.2.1 | Review/Update Plan
0.2.2 | Describe Basic Use Cases
0.2.3 | Create Domain Model
0.2.4 | Plan/Start Database Development
0.2.5 | Plan/Start GUI Development
0.3 | Phase 3
0.3.1 | Review/Update Plan
0.3.2 | Update Domain Model
0.3.3 | Expand Use Cases
0.3.4 | Design Robustness Diagrams
0.3.5 | Continue GUI Development
0.4 | Phase 4
0.4.1 | Update Domain Model
0.4.2 | Update Robustness Diagrams
0.4.3 | Create Sequence Diagrams
0.4.4 | Complete Core DB Development
0.4.5 | Basic Matching Algorithm Design
0.4.6 | Complete Core GUI Development
0.5 | Phase 5
0.5.1 | Create Class Diagram
0.5.2 | Design Test Scenarios
0.5.3 | Develop Matching Algorithm
1.0 | Final Phase
1.0.1 | Review/Update All Documentation
1.0.2 | Finalize/Run Test Scenarios
1.0.3 | Finish Up Feature Development