## Gantt Chart Template
GANTT CHART
| PROJECT TITLE | PROJECT CONCORD
| DATE | 12/03/2022
[6 empty] | PROTOTYPE PHASE |  |  |  |  | MINIMUM VIABLE PRODUCT PHASE | [11 empty] | TESTING PHASE
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION (DAYS) | PCT OF TASK COMPLETE | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST
[6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
100%
1 | Prototype Phase
1.1 | Document System Requirements | 2022-03-01 | 2022-03-03 | 2 | 0% | bar: MARCH W1
1.2 | Compose Detailed Description | 2022-03-04 | 2022-03-09 | 3 | 0% | bar: MARCH W1
1.3 | Discuss Features/Capabilities | 2022-03-03 | 2022-03-08 | 2 | 0% | bar: MARCH W1
1.4 | Task Assignment/Planning | 2022-03-10 | 2022-03-17 | 5 | 0% | bar: MARCH W2
1.5 | User Interface Design | 2022-03-18 | 2022-04-08 | 15 | 0% | bar: MARCH W3 to APRIL W1
1.6 | User Experience Design | 2022-03-18 | 2022-04-01 | 10 | 0% | bar: MARCH W3 to MARCH W4
2 | Minimum Viable Product Phase
2.1 | User Input Processing | 2022-04-11 | 2022-05-09 | 20 | 0% | bar: APRIL W2 to MAY W1
2.2 | Front End Logic | 2022-04-11 | 2022-05-02 | 15 | 0% | bar: APRIL W2 to APRIL W4
2.3 | Database | 2022-04-11 | 2022-05-02 | 15 | 0% | bar: APRIL W2 to APRIL W4
2.4 | User Interface | 2022-05-10 | 2022-06-07 | 20 | 0% | bar: MAY W2 to JUNE W1
2.5 | User Management System | 2022-05-03 | 2022-05-31 | 20 | 0% | bar: MAY W1 to MAY W4
2.6 | Matching Algorithm | 2022-05-03 | 2022-06-07 | 25 | 0% | bar: MAY W1 to JUNE W1
2.8 | Push Notifications | 2022-06-08 | 2022-06-15 | 5 | 0% | bar: JUNE W2
2.7 | Intermediary Modules | 2022-06-16 | 2022-07-07 | 15 | 0% | bar: JUNE W3 to JULY W1
3 | Testing Phase
3.1 | Testing | 2022-07-08 | 2022-07-22 | 10 | 0% | bar: JULY W2 to JULY W4
3.2 | Design Revisions | 2022-07-25 | 2022-08-03 | 7 | 0% | bar: JULY W4
3.3 | Bug Fixes | 2022-07-25 | 2022-08-08 | 10 | 0% | bar: JULY W4 to AUGUST W1
3.4 | Product Launch | 2022-08-09 | 2022-08-16 | 5 | 0% | bar: AUGUST W2