## Gantt Chart Template
GANTT CHART | [26 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | PROJECT CONCORD
| DATE | 12/03/2022
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [13 empty] | PHASE THREE | [15 empty] | PHASE FOUR | [25 empty] | PHASE FIVE | [18 empty] | PHASE SIX
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [7 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [8 empty] | WEEK 7 |  |  |  |  | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 |  |  |  |  | WEEK 14
[6 empty] | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su
[5 empty] | 100% | WEEK 1 F: 4/3; WEEK 2 F: 18/3; WEEK 3 Sa: 19/3; WEEK 4 F: 1/4; WEEK 5 Sa: 2/4; WEEK 6 Su: 17/4; WEEK 7 M: 18/4; WEEK 10 F: 13/5; WEEK 11 Sa: 14/5; WEEK 13 W: 1/6; WEEK 14 Th: 2/6; WEEK 14 Su: 12/6
0.1 | Phase 1
0.1.1 | Compose Detailed Description | 2022-03-01 | 2022-03-11 | 10 | 0% | bar: WEEK 1 F to WEEK 1 F
0.1.2 | Create PERT / Gantt Charts | 2022-03-12 | 2022-03-15 | 3 | 0% | bar: WEEK 2 Sa to WEEK 2 Tu
0.1.4 | Compose Risk Assessment/ Team RA | 2022-03-12 | 2022-03-15 | 3 | 0% | bar: WEEK 2 Sa to WEEK 2 Tu
0.1.5 | Compose Feasibility Study | 2022-03-12 | 2022-03-17 | 5 | 0% | bar: WEEK 2 Sa to WEEK 2 F
0.2 | Phase 2
0.2.1 | Review/Update Plan | 2022-03-19 | 2022-03-21 | 2 | 0% | bar: WEEK 3 Sa to WEEK 3 M
0.2.2 | Describe Basic Use Cases | 2022-03-21 | 2022-03-24 | 3 | 0% | bar: WEEK 3 Tu to WEEK 3 F
0.2.3 | Create Domain Model | 2022-03-25 | 2022-03-27 | 2 | 0% | bar: WEEK 3 F to WEEK 4 M
0.2.4 | Plan/Start Database Development | 2022-03-28 | 2022-03-30 | 2 | 0% | bar: WEEK 4 Tu to WEEK 4 F
0.2.5 | Plan/Start GUI Development | 2022-03-28 | 2022-03-31 | 3 | 0% | bar: WEEK 4 Tu to WEEK 4 F
0.3 | Phase 3
0.3.1 | Review/Update Plan | 2022-04-02 | 2022-04-04 | 2 | 0% | bar: WEEK 5 Sa to WEEK 5 M
0.3.2 | Update Domain Model | 2022-04-05 | 2022-04-07 | 2 | 0% | bar: WEEK 5 Tu to WEEK 5 Th
0.3.3 | Expand Use Cases | 2022-04-05 | 2022-04-07 | 2 | 0% | bar: WEEK 5 Tu to WEEK 5 Th
0.3.4 | Design Robustness Diagrams | 2022-04-07 | 2022-04-10 | 3 | 0% | bar: WEEK 5 F to WEEK 6 M
0.3.5 | Continue GUI Development | 2022-04-11 | 2022-04-16 | 5 | 0% | bar: WEEK 6 Tu to WEEK 6 Su
0.4 | Phase 4
0.4.1 | Update Domain Model | 2022-04-18 | 2022-04-21 | 3 | 0% | bar: WEEK 7 M to WEEK 7 Th
0.4.2 | Update Robustness Diagrams | 2022-04-21 | 2022-04-26 | 5 | 0% | bar: WEEK 7 F to WEEK 8 W
0.4.3 | Create Sequence Diagrams | 2022-04-21 | 2022-04-28 | 7 | 0% | bar: WEEK 7 F to WEEK 8 Th
0.4.4 | Complete Core DB Development | 2022-04-29 | 2022-05-06 | 7 | 0% | bar: WEEK 8 F to WEEK 9 F
0.4.5 | Basic Matching Algorithm Design | 2022-04-29 | 2022-05-09 | 10 | 0% | bar: WEEK 8 F to WEEK 10 Tu
0.4.6 | Complete Core GUI Development | 2022-04-29 | 2022-05-13 | 14 | 0% | bar: WEEK 8 F to WEEK 10 F
0.5 | Phase 5
0.5.1 | Create Class Diagram | 2022-05-14 | 2022-05-18 | 4 | 0% | bar: WEEK 11 Sa to WEEK 11 W
0.5.2 | Design Test Scenarios | 2022-05-19 | 2022-05-29 | 10 | 0% | bar: WEEK 11 Th to WEEK 13 Su
0.5.3 | Develop Matching Algorithm | 2022-05-19 | 2022-06-01 | 12 | 0% | bar: WEEK 11 Th to WEEK 13 W
1.0 | Final Phase
1.0.1 | Review/Update All Documentation | 2022-06-04 | 2022-06-06 | 2 | 0% | bar: WEEK 14 Th to WEEK 14 M
1.0.2 | Finalize/Run Test Scenarios | 2022-06-07 | 2022-06-09 | 2 | 0% | bar: WEEK 14 Tu to WEEK 14 F
1.0.3 | Finish Up Feature Development | 2022-06-07 | 2022-06-10 | 3 | 0% | bar: WEEK 14 Tu to WEEK 14 Su