## Gantt Chart Template
| GANTT CHART | [21 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | PROJECT CONCORD
| DATE | 12/04/2022
|  | PROTOTYPE PHASE |  |  |  |  | MINIMUM VIABLE PRODUCT PHASE | [11 empty] | TESTING PHASE
| TEAM MEMBER | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
GEORGIOS AGGELOPOULOS
|  | 1.2 | 1.4 |  |  |  |  | 2.2 | [5 empty] | 2.4 |  |  |  | 2.8 |  |  | 3.2 |  | 3.4
|  | 1.3 |  |  | 1.6 |  |  |  |  | 2.1 | [9 empty] | 3.1
VASILIOS DELALIS
|  | 1.1 | [5 empty] | 2.1 | [5 empty] | 2.6 |  |  | 2.8 |  |  |  |  | 3.3
|  | 1.3 |  |  |  | 1.5 |  |  | 2.3 | [10 empty] | 3.1
NIKOLAOS KANTAS
|  | 1.1 | [5 empty] | 2.3 | [5 empty] | 2.4 |  |  | 2.8 | [5 empty] | 3.4
|  | 1.3 |  |  |  | 1.5 |  |  |  | 2.1 | [10 empty] | 3.1
MARIA KONSTANTINA BIZOUMI
|  | 1.2 | 1.4 |  |  |  |  | 2.1 |  |  |  |  | 2.5 |  | 2.7 |  |  | 2.8 |  |  | 3.2 |  | 3.4
|  | 1.3 |  |  | 1.6 |  |  |  | 2.2 | [10 empty] | 3.1
ALEXANDROS PANAGIOTIS SOILEMEZIDIS
|  | 1.2 | [6 empty] | 2.2 | [5 empty] | 2.7 |  |  | 2.8 |  |  |  | 3.3
|  | 1.3 |  |  |  | 1.5 | [6 empty] | 2.5 | [6 empty] | 3.1
WBS LEGEND
WBS NUMBER | TASK TITLE
1 | Prototype Phase
1.1 | Document System Requirements
1.2 | Compose Detailed Description
1.3 | Discuss Features/Capabilities
1.4 | Task Assignment/Planning
1.5 | User Interface Design
1.6 | User Experience Design
2 | Minimum Viable Product Phase
2.1 | User Input Processing
2.2 | Front End Logic
2.3 | Database
2.4 | User Interface
2.5 | User Management System
2.6 | Matching Algorithm
2.7 | Push Notifications
2.8 | Intermediary Modules
3 | Testing Phase
3.1 | Testing
3.2 | Design Revisions
3.3 | Bug Fixes
3.4 | Product Launch